SECTION 01 34 00

REQUESTS FOR INTERPRETATION (RFI)

PART 1 - GENERAL

1.1	RELATED DOCUMENTS

A.	Construction Drawings, Technical Specifications, Addenda, and general provisions of the Contract, including Contract General Conditions and Supplementary General Conditions and other Division 1 Specification Sections, apply to this Section.

1.2	SECTION INCLUDES

A.	Procedures for submitting requests for interpretation (RFI).

B.	Limitations on use of RFI to obtain interpretation and clarification.

1.3	RELATED SECTIONS

A.	Section 01 31 00 - Coordination:  Requirements for organizing and coordinating the Work.

B.	Section 01 33 00 - Submittals Procedures:  Restriction on use of submittals for changes in materials, products, equipment and systems.

C.	Section 01 63 00 - Product Substitution Procedures:  Procedures for requesting substitutions of materials, products, equipment and systems.

1.4	DEFINITIONS

A.	Request for Interpretation:  A document submitted by the Contractor requesting clarification of a portion of the Contract Documents, hereinafter referred to as an RFI.

1.5	PREBID REQUESTS FOR INTERPRETATION (PREBID RFIS)

    - Bidders shall use the enclosed form titled, ”Request for Interpretation of Contract Documents During Bid.” to submit written requests for interpretation or corrections by e-mail or fax to the University:

Cal Poly State University

Attn:  [Project Manager Name]

E-mail: [email]@calpoly.edu

Fax: (805) 756-####

    - To expedite the interpretation process, interpretations will be e-mailed to bidders as addenda.

    - Information shall be printed or typed including:  Company name, address, phone, Email address, contact person, date, time of request, and question or clarification.

    - If bidders have several questions that will not fit on one form, submit additional pages, numbering each page.

    - Deadline for Requests for Interpretation during bid period:  Requests for interpretation shall be received by the Trustees not later than ten (10) calendar days before the date bids will be opened.

    - The person submitting the request shall be responsible for its delivery.

1.6	CONTRACTOR'S REQUESTS FOR INTERPRETATION (RFIs) POST AWARD

A.	Contractor's Requests for Interpretation (RFIs):  Should Contractor be unable to determine from the Contract Documents the exact material, process, or system to be installed; or when the elements of construction are required to occupy the same space (interference); or when an item of Work is described differently at more than one place in the Contract Documents; the Contractor shall request that the Architect make an interpretation of the requirements of the Contract Documents to resolve such matters.  Contractor shall comply with procedures specified herein to make Requests for Interpretation (RFIs).

B.	Submission of RFIs:  RFIs shall be prepared and submitted electronically utilizing the Electronic Project Management System.  Refer to specification section 01 32 00. [IF IS NOT USED – REVISE THIS SECTION]

1.	Forms shall be completely filled in, and if supplemental drawings or other information is prepared by hand, it shall be fully legible.

2.	Each RFI shall be given a discrete, consecutive number.  Revised RFI shall include the original number with the addition of a decimal and subsequent revision number.  For instance, Revision #1 to RFI 029 should be noted as RFI 029.1.

3.	Each page of the RFI and each attachments to the RFI shall bear the University's project name, project number, date, RFI number and a descriptive title.

4.	Contractor shall attest to good faith effort to determine from the Contract Documents the information requested for interpretation.  Frivolous RFI or simply passing on the RFI to the University without first vetting the RFI shall be subject to reimbursement from Contractor to University for fees charged by University, the Architect, Architect's consultants and other design professionals engaged by the University.

C.	Subcontractor-Initiated and Supplier-Initiated RFIs:  RFIs from subcontractors and material suppliers shall be submitted through, be reviewed by and be attached to an RFI prepared, signed and submitted by Contractor.  RFIs submitted directly by subcontractors or material suppliers will be returned unanswered to the Contractor.

1.	Contractor shall review all subcontractor- and supplier-initiated RFIs and take actions to resolve issues of coordination, sequencing and layout of the Work.  Coordination of the work, sequence and layout are not the responsibility of the University or Architect.

2.	RFIs submitted to request clarification of issues related to means, methods, techniques and sequences of construction or for establishing trade jurisdictions and scopes of subcontracts will be returned without interpretation.  Such issues are solely the Contractor's responsibility.

3.	Contractor shall be responsible for delays resulting from the necessity to resubmit an RFI due to insufficient or incorrect information presented in the RFI.

D.	Requested Information:  Contractor shall carefully study the Contract Documents, in particular, Article 5 of the Contract General Conditions, to ensure that information sufficient for interpretation of requirements of the Contract Documents is not included.  RFIs that request interpretation of requirements clearly indicated in the Contract Documents will be returned without interpretation.

1.	In all cases in which RFIs are issued to request clarification of issues related to means, methods, techniques and sequences of construction, for example, pipe and duct routing, clearances, specific locations of Work shown diagrammatically, apparent interferences and similar items, the Contractor shall furnish all information required for the Architect or University's Representative to analyze and/or understand the circumstances causing the RFI and prepare a clarification or direction as to how the Contractor shall proceed.

2.	If information included with this type RFI by the Contractor is insufficient, the RFI will be returned unanswered.

E.	Unacceptable Uses for RFIs:  RFIs shall not be used to request the following:

1.	Approval of submittals (use procedure specified in Section 01 33 00 - Submittals Procedures)

2.	Approval of substitutions (refer to Section 01 63 00 - Product Substitution Procedures)

3.	Changes that entail change in Contract Time and Contract Sum (comply with provisions of the Contract General Conditions, as discussed in detail during pre-construction meeting)

4.	Different methods of performing Work than those indicated in the Contract Drawings and Specifications (comply with provisions of the Contract General Conditions).

F.	Disputed Requirements:  In the event the Contractor believes that a clarification by the University's Representative results in additional cost or time, Contractor shall comply with Article 5 of the Contract General Conditions.

G.	RFI Log:  The Electronic Project Management System will maintain a log of RFIs.  Only the University may close any outstanding RFI.

H.	Review Time:  Architect will return RFIs to Contractor and University's Representative within seven calendar days of receipt.  RFIs received after 12:00 noon shall be considered received on the next regular working day for the purpose of establishing the start of the seven-calendar day response period.  Additional time shall be granted depending on the complexity of the request.

PART 2 - PRODUCTS

Not Applicable to this Section.

PART 3 - EXECUTION

Not Applicable to this Section.

END OF SECTION

CALIFORNIA POLYTECHNIC STATE UNIVERSITY

REQUEST FOR INTERPRETATION OF CONTRACT DOCUMENTS DURING BID

To:	California Polytechnic State University

Attn:	[First Last Name] ([email]@calpoly.edu, Fax (805) 756-7566)

Project:	[Project title and Project Number]

Date:					Time:

Company:

Contact Person:

Address:

Telephone:							Email:

Plan Sheet:							Specification Section:

INTERPRETATION REQUESTED:

RESPONSE:

Date:					Time:

Company:

Contact Person:

INTERPRETATION: